## Application
North London Community Fund Application Spreadsheet
This spreadsheet contains three tables, one each for you to break down your project targets (what you plan to achieve), timeline (when everything will happen) and budget (how you will spend the funding). We ask you to fill this out is so that we can best understand what you want your project to achieve, and how. This sheet is designed to help you to ensure your project plan is clear, and that these three key elements are consistent with one another, as this is something your application will be evaluated on. There are step by step instructions to explain what you should put in each box. There is also a video on the application form that will talk you through each step. As with the application form, most of the questions here relate directly to sections of the evaluation criteria. Where this is true, you will see that it has been indicated in the column heading. This is to remind you of exactly what each answer will be evaluated against. If you have not done so already, you are encouraged to familiarise yourself with the evaluation criteria before you attempt to fill this application. Once you have completed all three tables in this spreadsheet, please download it, and attach it to your application form before you submit. Your application will be anonymised when it is evaluated. For this reason, we ask that you avoid putting any names, either of your team or of the project itself anywhere on this sheet. If you are having any difficulty, please reach out to wastepreventionteam@nlwa.gov.uk.
Step 1: Project Targets
Description | Target This column refers to evaluation criteria 2.1: Are the proposed outputs clear, specific and achievable? (Please include realistic estimates, such as the number of people you plan to engage, workshops or events you will run, or activities you will deliver) | Measurement This column refers to evaluation criteria 2.2: How will you collect data, feedback or evidence to measure the outcomes? | Role responsible This column refers to evaluation criteria 1.3: Who will deliver the project, and what relevant experience, skills, partnerships or resources do they bring?
Bicycles salvaged and redistributed through repair and reuse | 100 | We have a log book that will be used to record bikes donated to us, bikes we have fixed and those that are redistributed | Project lead will manage partnerships with local collection ponts, as well as assisting with repairs and community engagement. 2X part time paid staff will assist with collection, repair and distribution of bicycles. Staff members have been on the team for 3 and 5 years respectively. One is a bicycle mechanic by trade, the other a hobbiest but both are skilled and have a proven track record of bicycle repair. One member of staff will also be assisting with engagement through social media, which they have been responsible for for the last year.
Step 2: Project Timeline
Month | What we plan to deliver This column refers to evaluation criteria 1.2: What is the project timeline, including key milestones and delivery stages | Which project targets will be achieved? This column refers to evaluation criteria 1.2: What is the project timeline, including key milestones and delivery stages
2027-04-01 | Planning phase 1: Recruitment of workshop facilitator Bicycle collection/donations begins Promotion over social media Monthly cycle and social 12/04/2027 | 2/20 new attendees at cycle and social
Step 3: Project Budget
Item/Services to be purchased | Planned cost | Description This column refers to evaluation criteria 3.1: Is your budget realistic for what you plan to deliver, and are costs clearly explained and justified? And evaluation criteria 3.4: Staff time can be charged at a maximum of £20 per hour. External contractors delivering specialist services may be charged up to £25 per hour, provided the higher rate is fully justified. | Legacy This column refers to evaluation criteria 3.2: If you are purchasing equipment or materials, are these essential and good value? Could they be sourced second-hand, borrowed, shared or reused? How will any equipment purchased continue to provide value beyond the lifetime of the project?
Staff time (Project lead) | 2300 | Lead project manager - Responsible for managing partnerships with local collection points, as well as assisting with repairs and community engagement - 115hrs @ £20ph = £2300.00 | N/A
Tools for workshops | 500 | These are the tools participants will use when attending our training workshops. Workshop maximum capacity will be 15 people, and people can share, so to ensure we have enough we will need: Basic spanner set X8 ~ £10/15 = ~£100 Torx/Hex wrench set X8 ~ £20 = ~£160 Bike multitool X8 ~ £20 = ~£160 Puncture repair kits X 15 ~£5 = £75 (More required as these are not reusable) | Spanners, wrench sets and multitools will be purchased secondhand online from websites like Gumtree and Ebay. This will mean some irregularity in size.style, quality, but for the purposed of basic bike maintenance will work well. Puncture repair kits will need to be purchased brand new as these are not reusable. At the end of the project, tools will be distributed for free to the attendees or along with the bikes we donate, on a first come first served basis until all are gone.
Total | 0
Some things things to think about:
Staff time - (PAYE) Can be charged at a maximum of £20 per hour.
External contractors delivering specialist services may be charged up to £25 per hour, provided the higher rate is fully justified.
Contingency - You are permitted to include a contingency in your budget. However, we ask that you provide some explanation to justify what you anticipate this might be required for. Where relevant, please consider whether any risks to your project identified need to be reflected in a contingency here. Payment terms for this will be discussed in your kick-off meeting.
Next, move onto Step 2: Project Timeline
How to fill out this section:
Break down the specific deliverables of your project. Eg: What activities you will deliver, how many, how many people do you intend to engage, etc. Effectively, what are the measurable outputs and outcomes of your project? There's no set requirement for number of targets we expect to see, but as a guideline we recommend approximately 3-4 targets for micro grants, 4-6 targets for small and 5-8 for medium.
Description: Briefly describe the target/outcome you want to achieve.
Target: Give a specific figure you want to aim for. Eg: Number of workshops you will deliver, number of attendees you will reach, % of attendees who have reported a change since your activity. This will give you a clear goal to measure the progress of your project against.
Measurement: How will you measure and evidence your progress against each target. Eg: attendance records, participant surveys, feedback forms, case studies, social media engagement, volunteer logs, or any other methods you will use to monitor and report on project progress.
Role responsible: Demonstrate that you have the appropriate team to deliver the project you are proposing. For each target, explain who on your team will be responsible for delivering, monitoring and recording, and what experience this person holds that will ensure they are capable of undertaking that task effectively.
To maintain anonymity, please do not use identifiable names on this form - simply put the person's role within the team eg: Project lead, social media officer, external facilitator etc.
If you have not yet recruited the person responsible, please indicate this in the description. If hiring staff is something you need to do, consider this when completing your timeline below.
How to fill this section:
Break down your proposed budget. Give as much detail as possible to explain exactly how you intend to use the grant money. We expect that some items here will be an estimation rather than exact.
Items/services to be purchased: Explain briefly what items/services you intend to purchase
Planned cost: State the value. Be as accurate as you can, but its OK if you don't know the exact amount yet. The total at the bottom will automatically update.
When you are finished this should match the amound you are requesting. If it seems wrong - double click on the Total box where the figure is shown and make sure the formula includes all of your rows, and not the examples!
Description: Give more explanation of what this item is for and how it relates back to your project. Eg: If you are adding staff time, break down how you have calculated this, and relate it back to the roles each staff member will be carrying out. If you are adding items you need to purchase, try to explain the purpose of each of these for achieving your project targets.
Legacy: Consider the sustainability of items purchased for the project and how you will prevent materials bought from becoming waste themselves. Items may need to be purchased brand new, but applications will be viewed favourably where consideration has been taken to utilise secondhand or repurposed items, or borrowing rather than buying when possible/practical.
Where items have been bought new, try to demonstrate that you have considered their lifespan after the project concludes. Will the item remain in use, or be donated, repurposed etc?
Please note: This might not be relevant for all the items and is an optional column.
How to use this section:
Explain when the main activities in your project plan are expected to take place. Specific dates aren't a requirement at this stage, just explain roughly when you expect to be delivering what. This form is structured to encourage you to refer back to your project targets in your timeline.
Month: Add the month you are referring to.
What we plan to deliver: Describe what activities you intend to take place that month. If you know specific dates at this stage, please provide them, but don't worry if you can't. Consider the key milestones and stages of your project delivery, Eg: 'Phase 1: Planning, recruitment and purchasing of materials, Phase 2: Delivery of first round of workshops' etc.
Which project targets will be achieved: Refer back to your overall target outcomes here if you can. For some months this might not be relevant, but think about how far along with each target you expect to be at each stage of your timeline. Eg: If you have set a target to deliver 20 workshops in total across the project, by month 2 you might expect to have delivered 4.
Finally, move onto Step 3: Project Budget
Application Spreadhseet complete!
That's everything for this spreadhseet. Once you have filled all three tables with as much detail as you can, please download it, and upload it to your application form on Jotform before you submit everything.
Examples provided:
Boxes shaded this colour contain examples we have provided to help you answer the questions.
Please either replace them, or ignore them and fill your own answers in below.
These are just examples. Do not feel pressured to replicate them exactly.