## Application
North London Community Fund Application Spreadsheet
This spreadsheet contains three tables, one each for you to break down your project targets (what you plan to achieve), timeline (when everything will happen) and budget (how you will spend the funding). We ask you to fill this out is so that we can best understand what you want your project to achieve, and how. This sheet is designed to help you to ensure your project plan is clear, and that these three key elements are consistent with one another, as this is something your application will be evaluated on. There are step by step instructions to explain what you should put in each box. There is also a video on the application form that will talk you through each step. As with the application form, most of the questions here relate directly to sections of the evaluation criteria. Where this is true, you will see that it has been indicated in the column heading. This is to remind you of exactly what each answer will be evaluated against. If you have not done so already, you are encouraged to familiarise yourself with the evaluation criteria before you attempt to fill this application. Once you have completed all three tables in this spreadsheet, please download it, and attach it to your application form before you submit. Your application will be anonymised when it is evaluated. For this reason, we ask that you avoid putting any names, either of your team or of the project itself anywhere on this sheet. If you are having any difficulty, please reach out to wastepreventionteam@nlwa.gov.uk.
Step 1: Project Targets
Description | Target This column refers to evaluation criteria 2.1: What specific outcomes will your project achieve (e.g., how many people do you plan to engage with, how many workshops/events will you run)? | Measurement This column refers to evaluation criteria 2.2: How will you collect data, feedback or evidence to measure the outcomes? | Role responsible This column refers to evaluation criteria 1.3: Who will deliver the project, and what relevant experience, skills, partnerships or resources do they bring?
Bicycles salvaged and redistributed through repair and reuse | 100 | We have a log book that will be used to record bikes donated to us, bikes we have fixed and those that are redistributed | Project lead will manage partnerships with local collection ponts, as well as assisting with repairs and community engagement.
2X part time paid staff will assist with collection, repair and distribution of bicycles. Staff members have been on the team for 3 and 5 years respectively. One is a bicycle mechanic by trade, the other a hobbiest but both are skilled and have a proven track record of bicycle repair. One member of staff will also be assisting with engagement through social media, which they have been responsible for for the last year.
Bicycles redistributed provided to residents from minority communities or who do not currently own one | 50% | Anonymous surveys will be requested as part of the bicycle request form. These questions will not be mandatory so that potential participants are not discouraged | Project lead will be primarily responsible for community outreach, assited by part time staff who will manage social media and registers
Residents trained in basic bicycle repair and maintenance skills | 150 | We will be taking a register at the start of each session, as well as monitoring sign ups online | External paid facilitator (not yet recruited) will deliver workshops on our behalf. Facilitators will have DBS certificates and will be able to demonstrate 2+ years of previous community facilitation
Project lead will attend workshops to ensure everything runs smoothly and assist with facilitation
Deliver bicycle repair and maintenance workshops | 12 | Events will be monitored and recorded in our activity log | External paid facilitator (not yet recruited) will deliver workshops on our behalf. Facilitators will have DBS certificates and will be able to demonstrate 2+ years of previous community facilitation
Project lead will attend workshops to ensure everything runs smoothly and assist with facilitation
Engage new, regular attendees at our monthly cycle and social | 20 | Details will be taken during sign up, and checked against a register at the start of each session | These events are organised and lead by one of our part time members of staff, who has a full DBS and has been leading this group for 3 years.
Step 2: Project Timeline
Month | What we plan to deliver This column refers to evaluation criteria 1.2: What is the project timeline, including key milestones and delivery stages | Which project targets will be achieved? This column refers to evaluation criteria 1.2: What is the project timeline, including key milestones and delivery stages
2027-04-01 | Planning phase 1: Recruitment of workshop facilitator Bicycle collection/donations begins Promotion over social media Monthly cycle and social 12/04/2027 | 2/20 new attendees at cycle and social
2027-05-01 | Planning phase 2: Development of workshop content agreed with facilitator Purchase of any required materials Continued promotion for attendees and donations over social media Monthly cycle and social 14/05/2027 | 4/20 new attendees at cycle and social
2027-06-01 | Delivery phase 1: First bike maintenance workshop delivered Surveys taken to assess diversity of attendees First bikes redistributed Monthly cycle and social (date TBC) | 1/12 bicycle repair workshops delivered 10/150 residents trained in bicycle repair techniques 5/100 bicycled redistributed to local residents 6/20 new attendees at cycle and social
2027-07-01 | Delivery phase 2: Second bike maintenance workshop delivered Continued bicycle collection and refurbishment Promotion through community centres and partner organisations Monthly cycle and social (date TBC) | 2/12 bicycle repair workshops delivered 25/150 residents trained in bicycle repair techniques 12/100 bicycles redistributed to local residents 8/20 new attendees at cycle and social
2027-08-01 | Delivery phase 3: Third bike maintenance workshop delivered Outreach at local summer community events Continued bicycle donations and redistribution Monthly cycle and social (date TBC) | 3/12 bicycle repair workshops delivered 40/150 residents trained in bicycle repair techniques 20/100 bicycles redistributed to local residents 10/20 new attendees at cycle and social
2027-09-01 | Delivery phase 4: Fourth bike maintenance workshop delivered Targeted promotion to families and young people Monitoring of redistribution to priority groups Monthly cycle and social (date TBC) | 4/12 bicycle repair workshops delivered 55/150 residents trained in bicycle repair techniques 30/100 bicycles redistributed to local residents 12/20 new attendees at cycle and social
2027-10-01 | Mid-project review: Fifth bike maintenance workshop delivered Review participant feedback and delivery approach Continued bicycle refurbishment and redistribution Monthly cycle and social (date TBC) | 5/12 bicycle repair workshops delivered 70/150 residents trained in bicycle repair techniques 40/100 bicycles redistributed to local residents 14/20 new attendees at cycle and social
2027-11-01 | Delivery phase 5: Sixth bike maintenance workshop delivered Additional outreach through faith groups and local networks Volunteer recruitment and training Monthly cycle and social (date TBC) | 6/12 bicycle repair workshops delivered 85/150 residents trained in bicycle repair techniques 50/100 bicycles redistributed to local residents 15/20 new attendees at cycle and social
2027-12-01 | Winter delivery phase: Seventh bike maintenance workshop delivered Winter bicycle safety and maintenance focus Continued redistribution programme Monthly cycle and social (date TBC) | 7/12 bicycle repair workshops delivered 100/150 residents trained in bicycle repair techniques 60/100 bicycles redistributed to local residents 16/20 new attendees at cycle and social
2028-01-01 | Delivery phase 6: Eighth bike maintenance workshop delivered New year promotion campaign Continued collection, refurbishment and redistribution of bicycles Monthly cycle and social (date TBC) | 8/12 bicycle repair workshops delivered 100/150 residents trained in bicycle repair techniques 70/100 bicycles redistributed to local residents 17/20 new attendees at cycle and social
2028-02-01 | Delivery phase 7: Ninth bike maintenance workshop delivered Ongoing outreach and recruitment of workshop participants Monthly cycle and social (date TBC) | 9/12 bicycle repair workshops delivered 115/150 residents trained in bicycle repair techniques 80/100 bicycles redistributed to local residents 18/20 new attendees at cycle and social
2028-03-01 | Delivery phase 8: Tenth bike maintenance workshop delivered Continued bicycle refurbishment and redistribution Collection of participant feedback and case studies begins Monthly cycle and social (date TBC) | 10/12 bicycle repair workshops delivered 130/150 residents trained in bicycle repair techniques 90/100 bicycles redistributed to local residents 19/20 new attendees at cycle and social
2028-04-01 | Project completion phase 1: Eleventh bike maintenance workshop delivered Final outreach activity to attract new participants Final bicycle donations collected and refurbished Monthly cycle and social (date TBC) | 11/12 bicycle repair workshops delivered 140/150 residents trained in bicycle repair techniques 95/100 bicycles redistributed to local residents 20/20 new attendees at cycle and social
2028-05-01 | Project completion and evaluation: Twelfth bike maintenance workshop delivered Final bicycle distributions completed Project evaluation and impact reporting completed Sustainability plan developed to continue activities beyond the grant period Monthly cycle and social (date TBC) | 12/12 bicycle repair workshops delivered 150/150 residents trained in bicycle repair techniques 100/100 bicycles redistributed to local residents 50% of bicycles redistributed to residents from minority communities or who do not currently own one 20/20 new attendees at cycle and social
Step 3: Project Budget
Item/Services to be purchased | Planned cost | Description This column refers to evaluation criteria 3.1: Is your budget realistic for what you plan to deliver, and are costs clearly explained and justified? And evaluation criteria 3.4: Staff time can be charged at a maximum of £20 per hour. External contractors delivering specialist services may be charged up to £25 per hour, provided the higher rate is fully justified. | Legacy This column refers to evaluation criteria 3.2: If you are purchasing equipment or materials, are these essential and good value? Could they be sourced second-hand, borrowed, shared or reused? And evalutaion criteria 3.3: If you’re purchasing equipment, how will the purchased items continue to provide value beyond the lifetime of the project (for example, through reuse, sharing, donation or future activities)?
Staff time (Project lead) | 2300 | Lead project manager - Responsible for managing partnerships with local collection points, as well as assisting with repairs and community engagement - 115hrs @ £20ph = £2300.00
External workshop facilitator | 900 | External facilitator - will deliver workshops on our behalf - 12X 2 hr workshops+ 1 hour prep @ £25ph = 12X (3X25) = £900.00. (Specialist skillset required)
Tools for workshops | 500 | These are the tools participants will use when attending our training workshops. Workshop maximum capacity will be 15 people, and people can share, so to ensure we have enough we will need: Basic spanner set X8 ~ £10/15 = ~£100 Torx/Hex wrench set X8 ~ £20 = ~£160 Bike multitool X8 ~ £20 = ~£160 Puncture repair kits X 15 ~£5 = £75 (More required as these are not reusable) | Spanners, wrench sets and multitools will be purchased secondhand online from websites like Gumtree and Ebay. This will mean some irregularity in size.style, quality, but for the purposed of basic bike maintenance will work well. Puncture repair kits will need to be purchased brand new as these are not reusable. At the end of the project, tools will be distributed for free to the attendees or along with the bikes we donate, on a first come first served basis until all are gone.
Bicycle parts | 2000 | Replacement parts required to refurbish donated bicycles for redistribution. Includes inner tubes, tyres, brake pads, cables, chains, lights, reflectors and lubricants. Estimated average cost of £20 per bicycle across 100 bicycles. | Wherever possible, parts will be salvaged from donated bicycles that cannot be repaired. New parts will only be purchased where necessary to ensure bicycles are safe and roadworthy. Any leftover parts will be retained by RoundAgain CIC for future bicycle repair activities.
Bicycle safety equipment | 1000 | Helmets, locks, high-visibility accessories and light sets provided alongside redistributed bicycles where needed. Helps reduce barriers to cycling and promotes safe use of refurbished bicycles. | Safety equipment will be distributed directly to project beneficiaries and remain in use long after the project ends, helping to support continued active travel.
Promotion and outreach materials | 500 | Design and printing of posters, flyers and banners, plus targeted social media advertising to recruit workshop participants, attract bicycle donations and promote the monthly cycle and social. | Printed materials will be produced on recycled paper where possible. Reusable banners and signage will be retained for future community repair and cycling projects.
Contribution to organisational core costs | 1200 | Contribution towards the overheads associated with delivering the project, including utilities, insurance, workshop space maintenance, administration, volunteer management and use of RoundAgain CIC's existing premises in Hackney and Waltham Forest. These costs enable the organisation to safely store donated bicycles, carry out repairs, host workshops and coordinate redistribution activities.
Volunteer expenses | 600 | Travel and refreshments for volunteers supporting collection, refurbishment, workshop delivery and event organisation. Supports volunteer recruitment and retention.
Monitoring and evaluation | 300 | Participant surveys, data collection, outcome monitoring and production of a final impact report. Includes printing and data management costs.
Bicycle collection and transport costs | 700 | Fuel, vehicle hire and transport costs associated with collecting donated bicycles and delivering refurbished bicycles to residents unable to collect them independently.
Total | 10000
Some things things to think about:
Staff time - (PAYE) Can be charged at a maximum of £20 per hour.
External contractors delivering specialist services may be charged up to £25 per hour, provided the higher rate is fully justified.
Contingency - You are permitted to include a contingency in your budget. However, we ask that you provide some explanation to justify what you anticipate this might be required for. Where relevant, please consider whether any risks to your project identified need to be reflected in a contingency here. Payment terms for this will be discussed in your kick-off meeting.
Next, move onto Step 2: Project Timeline
How to fill out this section:
Break down the specific deliverables of your project. Eg: What activities you will deliver, how many, how many people do you intend to engage, etc. Effectively, what are the measurable outputs and outcomes of your project? There's no set requirement for number of targets we expect to see, but as a guideline we recommend approximately 3-4 targets for micro grants, 4-6 targets for small and 5-8 for medium.
Description: Briefly describe the target/outcome you want to achieve.
Target: Give a specific figure you want to aim for. Eg: Number of workshops you will deliver, number of attendees you will reach, % of attendees who have reported a change since your activity. This will give you a clear goal to measure the progress of your project against.
Measurement: How will you measure and evidence your progress against each target. Eg: attendance records, participant surveys, feedback forms, case studies, social media engagement, volunteer logs, or any other methods you will use to monitor and report on project progress.
Role responsible: Demonstrate that you have the appropriate team to deliver the project you are proposing. For each target, explain who on your team will be responsible for delivering, monitoring and recording, and what experience this person holds that will ensure they are capable of undertaking that task effectively.
To maintain anonymity, please do not use identifiable names on this form - simply put the person's role within the team eg: Project lead, social media officer, external facilitator etc.
If you have not yet recruited the person responsible, please indicate this in the description. If hiring staff is something you need to do, consider this when completing your timeline below.
How to fill this section:
Break down your proposed budget. Give as much detail as possible to explain exactly how you intend to use the grant money. We expect that some items here will be an estimation rather than exact.
Items/services to be purchased: Explain briefly what items/services you intend to purchase
Planned cost: State the value. Be as accurate as you can, but its OK if you don't know the exact amount yet.
Description: Give more explanation of what this item is for and how it relates back to your project. Eg: If you are adding staff time, break down how you have calculated this, and relate it back to the roles each staff member will be carrying out. If you are adding items you need to purchase, try to explain the purpose of each of these for achieving your project targets.
Legacy: Consider the sustainability of items purchased for the project and how you will prevent materials bought from becoming waste themselves. Items may need to be purchased brand new, but applications will be viewed favourably where consideration has been taken to utilise secondhand or repurposed items, or borrowing rather than buying when possible/practical.
Where items have been bought new, try to demonstrate that you have considered their lifespan after the project concludes. Will the item remain in use, or be donated, repurposed etc?
Please note: This might not be relevant for all the items and is an optional column.
How to use this section:
Explain when the main activities in your project plan are expected to take place. Specific dates aren't a requirement at this stage, just explain roughly when you expect to be delivering what. This form is structured to encourage you to refer back to your project targets in your timeline.
Month: Add the month you are referring to.
What we plan to deliver: Describe what activities you intend to take place that month. If you know specific dates at this stage, please provide them, but don't worry if you can't. Consider the key milestones and stages of your project delivery, Eg: 'Phase 1: Planning, recruitment and purchasing of materials, Phase 2: Delivery of first round of workshops' etc.
Which project targets will be achieved: Refer back to your overall target outcomes here if you can. For some months this might not be relevant, but think about how far along with each target you expect to be at each stage of your timeline. Eg: If you have set a target to deliver 20 workshops in total across the project, by month 2 you might expect to have delivered 4.
Finally, move onto Step 3: Project Budget
Application Spreadhseet complete!
That's everything for this spreadhseet. Once you have filled all three tables with as much detail as you can, please download it, and upload it to your application form on Jotform before you submit everything.
Examples provided:
Boxes shaded this colour contain examples we have provided to help you answer the questions.
Please either replace them, or ignore them and fill your own answers in below.
These are just examples. Do not feel pressured to replicate them exactly.