Appendix B

PRG Criteria

Project review group criteria

| Criteria | Contents | Cross Reference to Relevant Section of OBC |
| --- | --- | --- |
| Affordability | Projected PFI service payments identified Shadow bid assumptions – CapEx, OpEx, lifecycle etc Comment on funding assumptions e.g. gearing The PFI credit support and the method of calculation Comment on all budgeted sources of income including any risks associated with the income assumptions (give careful consideration to 3rd party income assumptions) Are any land sales anticipated Confirmation that no capital payments from authority planned or why exceptional circumstances exist Affordable in the first full year, showing the unitary payment and matching sources of income Affordable over the whole life of the contract, taking into account all sources of income including existing LA resources, projected additional revenue support and additional income from capital receipts or third party income Review consistency of indexation assumptions Affordability analysis (base case and sensitivities), and impact on budgets, accepted by Members, Senior Management and budget holders. Detail supporting evidence (e.g. cabinet minutes) The assumption made of when PFI credits will start On-going affordability risks | Section 8 Appendix N |
| Design quality | Project to demonstrate how they intend to meet key objectives of the Egan Report (for example safety, minimising waste, supply chain management, etc) Authorities are expected to take account of the guidance on design quality included in the Department for Culture, Media and Sport’s (DCMS) publication 'Better Public Buildings', the OGC guidance 'How to achieve Design Quality in PFI Projects' and the 4ps 'Achieving Quality in Local Authority PFI Building Projects. Note any sector specific (e.g. housing, waste) design legislation / guidance and how it is to be followed Detail any involvement with Commission for Architecture and the Built Environment (CABE), whether the authority has appointed a “design champion” how good design will be addressed in the ISDS / Evaluation etc (e.g. through Design Quality Indicators) Has adequate consideration been given to design and whole life cost issues Consider the guidance on design provided in Appendix 7 of the PRG Code of Practice | Section 7.5 Appendices M, W and X. |
| Output specification | Requirement specified in terms of service outputs required, rather than particular assets or solutions Range of on-going services included in the requirement defined broadly, to offer scope for efficiencies and innovation Specification pitched at a level that is justifiable in terms of procurement best practice and robust precedent from similar projects, is consistent with affordability assumptions, and further enhancement in specification needs to demonstrate that value for money is not diminished Are specifications based on standard sector guidance (e.g. schools) Are the specifications based on previous projects, experience and good practice Is there anything either within or outside of the Project scope that is considered unusual | Section 4.9 Appendices W and X |
| Risk allocation | A PFI risk matrix has been prepared, identifying all the foreseeable risks associated with the scheme, and making a preliminary risk allocation Are risks allocated appropriately between the parties following standard form guidance including sector specific guidance where relevant such as 4Ps procurement packs Is there an Internal Risk Register identifying all risks to be managed by the public sector that ranks the lists in order of importance and a risk owner and mitigation strategy Is there regular reporting of risk management to the Project Board and is there a process to regularly update the risk register | Section 5 Appendices H, I, J and K. |
| Commercial interest | Evidence of commercial interest including approach to market sounding exercises Provide evidence of number of organisations contacted and response. Is there likely to be sufficient market interest in the project Are there factors which might hinder a good competition (e.g. geographic or sector related) Certainty of income stream to meet contract payments Willingness to consider appropriate opportunities for generation of other revenues, either from sales of assets or third party use of assets and services | Sections 4.6, 5.3.4, 5.4 and 9.4 Appendix G |
| Compliance with standard form | Commitment to use current version of SoPC terms and conditions or sector specific Standard Form where this has been approved Commitment to use the bidding process to embed standard Terms & Conditions Any likely project or sector specific derogations identified and a process in place to identify and deal with these issues | Sections 5.2, 5.3 and 5.6 |
| Value for money analysis | Has the department undertaken a stage 1 VFM analysis that identifies the sector or investment programme as suited to PFI procurement Has the authority completed the stage 2 quantitative and qualitative VFM assessment For the quantitative assessment have robust input costs, economic assumptions and risk assumptions for both the conventional and PFI solutions been applied Provide details of the quantitative VFM benefit and the sensitivity analysis / indifference points. Compare with other projects in the same sector Evidence that the stage 2 qualitative evaluation has been completed by the project team, is project specific and is supported by a good evidence base | Section 8.4 Appendix N |
| Suitability of advisors | Has the Authority identified all of the advisory support it will require Have advisors been appointed. If not when will they be appointed If the Authority is using in-house resources are they suitably skilled and experienced Who are the appointed advisors? What are the terms of the appointment and has a suitable budget been identified? Do the advisors have suitable sector specific experience Willingness of advisers to share lessons and approaches, without undue confidentiality and copyright constraints Arrangements for periodic review of performance of advisers | Sections 6.2, 6.3, 6.4 and 8.2 |
| Indicative timetable | Procurement timetable prepared Detail and total length and breakdown into component parts Timetable and affordability assumptions consistent Stages of procurement process kept to a minimum consistent with achieving optimal project delivery at least cost Total elapsed time from OJEU to completion realistic taking into account sector specific experience Timetable is consistent with previous experience within the sector | Section 10.2 |
| Project team | Project management experience. Provide specific details of previous PFI experience of the project team especially that of the Project Manager and Project Director Detail the numbers of full and part time resources both current and planned Appropriate range of skills and experience, whether from advisors or in house, for the deal envisaged Project team demonstrates capacity to undertake the procurement Is there a suitable project management structure including reporting lines to the Project Board and members Have suitable powers been delegated to the Project Team to effectively manage and progress the procurement Is there a project budget and if so is it sensible Accessible to involvement of 4Ps / Departmental PFU Recommendations from any recent gateway reviews plus info on how the authority has responded to these | Section 6.2, 6.3 and 6.4 Appendix GG |
| Commitment of sponsors, stakeholders & users | Demonstrable support from all key sponsors (such as Councilors and Senior Officers) and, where appropriate, users such as School Governors. Consultation with all other stakeholders Detail any relevant decision making processes Ensure consistency between support of stakeholders and affordability commitments Is there an effective communications strategy to liaise with all interested groups and keep them informed of progress / key decisions | Sections 3.1, 3.2, 6.2, 6.6, 9.1, 9.2.6, 9.5 Section 8.6 Appendices U and AA |
| Statutory process | Ensure statutory processes are either complete or factored into the timetable Note the relevant regulatory processes Consider risk of delay, need for public consultation etc Are sector specific issues adequately addressed Is there are mitigation strategy in place to manage statutory risks (especially relevant where planning may be contentious) Has the project got outline planning permission? Are there any other bodies which will have right to veto e.g. Mayor of London, Government Office for the South East etc. What consultation has taken place with these | Sections 3.1, 7.3.4, 5.3, 9.1, 9.2.6, 10 |